## PROJ PLAN
GOVERNMENT MCA COLLEGE MANINAGAR (569)
MCA SEM 6 PROJECT (4669301)
PROJECT WORK PLAN
project title: |  | Online Examination System
Team members name & enrollment no : |  | Nishant Karena (185693693012)
SR NO | MONTH | WORK PLANNED | WORK DONE | SUBMITTED BY | APPROVED BY | REMARKS
OCT 2021 | WEEK 3 | Project Definition | . | Nishant
| WEEK 4 | Platform and framework setup | . | Nishant
NOV 2021 | WEEK 1 | Analysis Directory structure and start working index page | . | Nishant
| WEEK 2 | done authention | . | Nishant
| WEEK 3 | add categories for exams | . | Nishant
| WEEK 4 | add questions and options | . | Nishant
DEC 2021 | WEEK 1 | user login and signup | . | Nishant
| WEEK 2 | working to improve ui | . | Nishant
| WEEK 3 | set timing for exam | . | Nishant
| WEEK 4 | create template for exam result | . | Nishant
JAN 2022 | WEEK 1 | database connections | . | Nishant
| WEEK 2 | connect database with project | . | Nishant
| WEEK 3 | working to improve ui | . | Nishant
| WEEK 4 | User profile | . | Nishant
FEB 2022 | WEEK 1 | User Results | . | Nishant
| WEEK 2 | login and resistration validation | . | Nishant
| WEEK 3 | login and resistration validation | . | Nishant
| WEEK 4 | implementing categories and qeustions | . | Nishant
MAR 2022 | WEEK 1 | Testing and error solving | . | Nishant
| WEEK 2 | Testing and error solving | . | Nishant
| WEEK 3 | Documention | . | Nishant
| WEEK 4 | Documention | . | Nishant